# Request for Quotes (RFQ)

# Punanga Nui Market Entertainment Stage Roof Replacement –

# (NEC4 Construction Contract)

The Cook Islands Investment Corporation (CIIC), the Client, invites suitably qualified Contractors to submit quotations for the replacement of the Punanga Nui Market (PNM) Entertainment Stage Roof Works.

The existing PNM Entertainment Stage Roof comprises timber trusses, plywood lining, timber battens and kikau thaching. The thatching has reached the end of its serviceable life and requires replacement.

The Scope of Works is outlined in the Description of the Works. Quotes shall be for the whole Scope of Works and in accordance with the Contract.

Key Dates

| Deadline for submission of Quotes: | 4.00pm Friday 07 August 2026 (CI Time) |
| --- | --- |
| Planned award notification: | 19 August 2026 |
| Proposed contract delivery period: | Commence on 22 August 2026. Complete no later that 28 August 2026. |

This document forms the Scope under NEC4 Engineering and construction short contract.

- Description of the Works

The Works involve the replacement of the Entertainment Stage Roof, including the removal of existing deteriorated kikau thatching and roofing materials, repairs to damaged plywood lining, installation of new purlins, prefinished corrugated metal roofing, associated flashings, gutters and downpipes.

The objective is to deliver a more functional, durable and coastal-suitable roofing system that provides a safe and reliable space for events, vendors and market users, while ensuring the Works are completed in accordance with relevant technical standards and manufacturer requirements.

### Scope of Works

The Contractor shall be responsible for the following:

- Remove and dispose of all existing kikau thatching and any existing roofing materials found to be deteriorated or damaged.

- Replace any sections of plywood lining found to be rotten, damaged, delaminated, or otherwise unsuitable for retaining as part of the new roofing system.

- Retain existing roof trusses and primary roof framing.

- Should any deterioration, structural defects, insect damage, or other concerns affecting the roof trusses or primary roof framing be identified, the Contractor shall immediately notify the Client and obtain direction prior to undertaking any remedial Works.

- Supply and install new 75 x 50mm timber purlins fixed on edge at maximum 600mm centres over the plywood lining. Purlins shall be securely fixed through the plywood lining into the underlying roof framing and installed to provide adequate support for the new roofing system.

- Supply and install new prefinished corrugated metal roofing sheets complete with all necessary accessories, closures, and fixings required to achieve a complete and weathertight roofing system.

- Roofing sheets shall be fixed to the purlins using minimum 75mm long stainless-steel roofing screws complete with cyclone caps, or approved equivalent, in accordance with the manufacturer's recommendations and applicable wind loading requirements.

- Supply and install all associated flashings, including ridge, barge, apron, and other flashings as required to provide a complete and weathertight installation. Flashings shall match the roofing profile, finish, and colour.

- Supply and install new gutters to both sides of the roof, including all brackets, stop ends, outlets, and associated fittings.

- Supply and install new downpipes to both sides of the roof, complete with all brackets, bends, shoes, and fittings necessary for a complete and operational stormwater disposal system.

- All roofing materials, flashings, gutters, downpipes, fixings, and accessories shall be suitable for use in a coastal environment and installed strictly in accordance with the manufacturer's recommendations.

- Upon completion of the Works, remove all debris, surplus materials, and waste from site and leave the work area clean and tidy.

- Please refer to the Drawings for more details and information.

### Drawings

The Drawings are attached separately to this RFQ Document:

| SHEET NUMBER | TITLE | REVISION NUMBER |
| --- | --- | --- |
| 1.1 | Cover Page | A |
| 1.2 | Existing Section View | A |
| 1.3 | Scope of Works | A |
| 1.4 | Proposed New Framing Plan | B |
| 1.5 | Proposed Repairs | B |

### Standards and Specifications

All roofing materials, flashings, gutters, downpipes, fixings and accessories shall be stuitable for use in a coastal environment and installed strictly in accordance with the manufacturer’s recommendations.

### Defects Liability and Remediation Requirements

The Contractor shall be responsible for any defects arising during the 12-month Defects Liability Period following completion of the Roof Replacement Works. This includes, but is not limited to:

- Water leaks, moisture ingress, or failures in the weathertightness of the roofing system.

- Defects relating to roofing sheets, flashings, gutters, downpipes, fixings, or associated components arising from workmanship or installation.

- Any deterioration, damage, or failure of the roofing system that affects its performance, durability, or safe operation.

The Contractor shall:

- Undertake inspections as required during the 12-month Defects Liability Period or as otherwise requested by the Client.

- Rectify identified defects within 14 days of notification, or earlier where the defect affects safety, functionality, or causes water ingress.

- Bear all costs associated with labour, materials, equipment, access requirements, and any other resources required to complete defect repairs.

- Exclusions

The following are excluded from this Contract:

- Stormwater Infrastructure assosciated with the new roof drainange system.

- The Contractor shall install new gutters and downpipes only. Downpipes shall terminate at ground level in the interim until connection to the stormwater network is completed under a separate Contract.

- Constraints

- No work is permitted on Sundays.

- The Contractor must allow access for other Contractors working on the site, if required.

- Requirements for the Programme

- The Planned commencement date for the Contract delivery is Saturday 22 August 2026, anticipated to commence immediately following the usual Saturday morning market day.

- The Entertainment Stage Roof shall remain unavailable for use throughout the duration of the Works.

- Roof Replacement Works shall be completed no later than Friday 28 August 2026.

- The Entertainment Stage shall be fully ready for use and operational for the market day on Saturday 29 August 2026.

- If the Contractor’s Work is delayed due to weather or unforeseen circumstances, the Client must be advised immediately and appropriate remediation measures shall be agreed upon to minimise delays and ensure completion within the required timeframe.

- The Contractor must provide a Quantity Survey (QS) for the full Scope of Works. This must also be submitted to and approved by the Client prior to the commencement of Works on Site.

- Contractor’s Methodology Requirements

Contractors must submit a methodology that includes:

- A proposed construction methodology and sequence for the roof replacement Works, including the removal of existing roofing materials and installation of the new roofing system.

- Details of two (2) similar projects demonstrating relevant experience in comparable roofing or building works.

- A proposed programme, including key milestones, timeframe and working hours.

- Site access arrangements, work area management, and any restrictions or measures proposed to safely undertake the orks while minimising disruption to Punanga Nui Market operations.

- Quality assurance procedures, including material specifications, installation methods, inspection and testing (where applicable), and confirmation that all Works will comply with the manufacturer's recommendations and relevant technical standards.

- Schedule of Prices

Contractors must submit the completed Pricing Template below:

| Item Number | Description | Price |
| --- | --- | --- |
| 1 | Full replacement Works of the Entertainment Stage Roof - Punanga Nui Market |  |
|  | VAT |  |
| The total of the Prices |  | NZ$ |

To be used for caluculating Variations:

| The fee percentage is |  | % |
| --- | --- | --- |

The people rates are:

| category of person |  |  | unit rate |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Supervision | Hour |  |  |  |
| Trained labour | Hour |  |  |  |
| General labour | Hour |  |  |  |

- Conflict of Interest Declaration

A conflict of interest arises if you or a close family member has an interest e.g. is a board or committee member or is employed in a senior position in the Government agency that wants to purchase the goods or services relating to this RFQ process.

In submitting this Quote I declare:

- That I understand an actual, potential or perceived conflict of interest may arise in participating in this Quote process and that I am obliged to declare any such conflict of interest.

- That in submitting this information that I have either declared any potential conflicts of interest or that I am not aware of any situation or issue that would conflict with the interest of the CIIC.

- If a conflict of interest arises at any time before the selected Respondent has been awarded the contract, I will advise the CIIC immediately.

- I have personally completed this declaration on behalf of the Respondent and declare that the submitted Quotes provided are true and correct.

I declare that I have a potential conflict of interest as follows:

| I will manage this conflict of interest by: |  |  |
| --- | --- | --- |
| Declared by: |  |  |
| Signature |  | Date |
| Full Name |  | Position (if Company) |

- Draft Contract

The Contract type is NEC4 Engineering and Construction Short Contract. The Draft Contract is attached separately to this RFQ Document.

- Further information or Site Visits

For any questions, please email tutemaeva.poaru@cookislands.gov.ck.

- Submission

All quotes shall be submitted on the Contractors Letterhead, and comprise:

- Contractor’s proposed Methodology Requirements (see section 5 above)

- Schedule of Prices (see section 6 above)

- Conflict of Interest Declaration

- Any proposed amendments to the Contract Works or Draft Contract

- Confirmation of capacity to deliver within the requested timeframe

All Quotes shall be submitted by email to tutemaeva.poaru@cookislands.gov.ck.